## Expediting Report
Khalda PO Number | Order No | Item Description | Quantity Ordered (Pcs) | Quantity Ordered (FT) | Khalda PO Date | Contractual Delivery Date | Current Status | Shipping Date | Expected Delivery Date | Reason For Delay And Actions
PO-2306 | SIGNOFF-2026-0011 | 7" 29# HP2 13CR95 KS Bear R3 SML | 20 | 800 | 24 Jun 26 | 17 Jul 26 | Closed | 29 Jun 26 | 17 Jul 26 | -